# ATTORNEY WORK PRODUCT — PRIVILEGED & CONFIDENTIAL

## ACTION SCHEDULE — Rahman v. UHSH et al., 3:26-cv-00197 (N.D.N.Y.)

Week-by-week sequencing, August → November 2026. Built 2026-08-02 solely from `data/action_items.json` (16 items), `data/pacing_digest.md`, and `strategy/MASTER_LEGAL_PLAN.md` §1. For Dr. Rahman and counsel (Drazen) only. Not for filing, service, or disclosure.

Labeling rules (binding): every dollar figure carries DOCUMENTED / ESTIMABLE / ASSERTED. The $100M anchor / $40M acceptance threshold are NEGOTIATION POSTURE ONLY (client directive) — never pleadable; Rule 11 / mediator-credibility caveat on every use; counsel approval required.

The two clocks (from MASTER_LEGAL_PLAN §1):

~Sept 2026 — MP state-tort rail (CPLR 215(3) [unverified — confirm with counsel], 1 yr from the Sept 2025 acquittal). GML 50-e(5) late-notice option closes ~Dec 2026 — decide by Nov.

Nov 2026 — court-ordered mediation must be completed; Drazen will not mediate without defendants' discovery responses.

Pacing rules applied (from `pacing_digest.md`): SoL-critical inputs first regardless of load, batched into single sittings; max 2 substantive tasks/week for Dr. Rahman; retrieval tasks batched into one low-effort block; emotionally heavy tasks never stacked, each followed by a light week; Haseeb owns the information-collection channel; cardiac device check scheduling is itself an action item — health before litigation.

Swim lanes: FR/SH rows = Dr. Faraaz Rahman (client, pacing-governed). DZ rows = Douglas Walter Drazen (counsel — not pacing-governed). HB rows = Haseeb Rahman (family information channel). Effort levels: Health / Light / Light-retrieval (batched) / Substantive / Heavy-emotional / Counsel / Family channel.

| Week | Items | Owner | Effort level | Why this week |
| --- | --- | --- | --- | --- |
| W1 · Aug 3–9 | ICD device check — schedule it (defibrillator unchecked ~3 years, DOCUMENTED lapse). NON-NEGOTIABLE, before any litigation task. | Dr. Rahman | Health | Health before litigation (pacing rule 5); the 3-year gap is itself a damages line (ICD-gap ≤$50K ESTIMABLE) |
| W1 | SoL-critical retrieval batch, one sitting: SH-01 names of the two complaint-filing doctors + two fired Indian physicians (with Dr. Mubeena Iqbal's contacts); FR-04 list of 2021/2022 official complaints against Dr. Ahmed; FR-05 print the senior resident's "don't complain" iMessages; hand counsel everything fixing the exact acquittal date + charging instrument (feeds Move 1 / DZ-02) | Dr. Rahman (+ mother on SH-01) | Light-retrieval (batched) | SoL-critical inputs go first regardless of load (pacing rule 1); the ~Sept 2026 MP rail is weeks away |
| W1 | Confirm exact acquittal date, charging instrument (information vs. indictment), and the NDNY scheduling-order amendment deadline (O-21); begin DZ-02 malicious-prosecution timeliness review; send preservation letters / spoliation notices (Guthrie, ANSCO CCTV, Nadeem phone) per Move 2 | Drazen | Counsel | The two highest-leverage unknowns (Move 1); "the timeliness of it now may be in question" (DZ-02) |
| W1 | HB-01 open the channel: begin collecting "all that information" incl. the "43 of the forgery" materials; establish the courier rhythm to Drazen; FAM-01 use the Verizon phone for all calls to Drazen | Haseeb | Family channel | Family carries the information-collection channel (pacing rule 4) so Faraaz's budget goes to substantive work |
| W2 · Aug 10–16 | FR-01 financial-records sitting (one sitting): bank records for father's ~$300K/yr transfers structured as loans (ESTIMABLE — $223.8K already DOCUMENTED via 38 hash-chained wires), Dubai cash medical payments, ~$1M living expenses (ESTIMABLE); locate the executed Florida contract ($350K salary + $70K bonus; $1.05M–$1.12M line — DOCUMENTED-PENDING/ASSERTED, Flag 4) in the same sitting | Dr. Rahman | Substantive (1 of 2) | Front-loads the financial-records gathering; the FL contract is the largest Tier 1 line and unusable externally until in counsel's hands (Move 3) |
| W2 | DZ-04 follow-up family call (via Verizon phone per FAM-01); on that call, clarify the FR-09 "$100 million with a base of 10" referent (unclear_referent — possibly ties to the $100M NEGOTIATION-POSTURE figure; never pleadable, Rule 11 caveat) | Dr. Rahman + Drazen | Light | Resolves Open Flag 5 cheaply while the call is happening anyway |
| W2 | DZ-01 finalize and serve plaintiff's discovery demands — academic record first (demand #1), then the ~14 consolidated demands (medical record, work-email access, comparator complaints, DA communications, Guthrie Apr 1–30 communications, subpoena copy, leave directives, Ahmed departure records, Nadeem texts, etc.) | Drazen | Counsel | Mediation is only worth attending with productions in hand (Move 2); responses must land before Nov |
| W2 | HB-01 continued: courier the financial records and exhibit materials to Drazen as Faraaz assembles them | Haseeb | Family channel | Keeps FR-01 output moving without adding load on Faraaz |
| W3 · Aug 17–23 | FR-02 academic-records markup: mark every unfair, inaccurate, or damaging entry; send markup to Drazen to frame the removal/correction demand. Scheduled alone — nothing else this week. | Dr. Rahman | Heavy-emotional (alone) | Feeds the record-correction relief (client's #1 objective, Grade A) and the amendment; emotionally heavy tasks are never stacked (pacing rule 3) |
| W3 | Draft the omnibus amendment (NY malicious prosecution, §1983 MP, NYSHRL + §296(6), FMLA-willful, Rehab Act); conclude DZ-02 review | Drazen | Counsel | Amendment unlocks the entire uncapped damages architecture (Move 1) |
| W3 | Light courier duty only | Haseeb | Family channel | Protects Faraaz's heavy week |
| W4 · Aug 24–30 | Light recovery week. One batched retrieval only: FR-03 search for the 2022 ten-page line-by-line GME rebuttal email (personal copy; the DZ-01 work-email demand is the fallback) | Dr. Rahman | Light-retrieval (batched) | Mandatory light week after FR-02 (pacing rule 3) |
| W4 | Finalize the omnibus amendment incorporating the FR-02 markup; target filing before end of August — hard stop ~Sept 2026 (O-1/O-21: never rely on relation-back; fallback is a protective state-court action) | Drazen | Counsel | The MP state-tort rail dies ~Sept 2026 |
| W4 | HB-01 close-out pass: confirm all "all that information" materials delivered, incl. "43 of the forgery" | Haseeb | Family channel | Everything counsel needs must be in hand before the amendment files |
| W5 · Aug 31–Sep 6 | FR-06 part 1: annotate the first half of the ~4,000-page saved-document archive | Dr. Rahman | Heavy (split) | Deliberately split across two weeks; never in the same week as FR-02 |
| W5 | File the omnibus amendment (if not already filed) — beats the ~Sept 2026 MP rail (1 yr from Sept 2025 acquittal) | Drazen | Counsel | Clock #1 |
| W6 · Sep 7–13 | FR-06 part 2: finish annotation and deliver the compiled document to Drazen; FR-07 initiate the ACGME complaint (Drazen: "that's fine") | Dr. Rahman | 2 × Substantive (at cap) | At the 2-task cap; ACGME is administrative leverage, not emotionally heavy, so no heavy-on-heavy stack; FR-06 delivery arms counsel for the discovery fight |
| W6 | Confirm amendment filed / rail beaten; chase discovery responses; issue third-party subpoenas (ANSCO CCTV, Nadeem carrier, Guthrie call-and-poster file, DA file / subpoena copy) | Drazen | Counsel | The three evidence keystones drive the probable-cause fight (Move 2) |
| W7 · Sep 14–20 | Light recovery week. Only item: attend/confirm the ICD device check appointment if it landed in September | Dr. Rahman | Health / Light | Mandatory light week after two loaded weeks; health items are first-class |
| W7 | Discovery-response window management; deficiency letters as responses arrive | Drazen | Counsel | Backward-planned from the Nov mediation deadline |
| W8 · Sep 21–27 | Work with counsel to resolve the Florida-contract execution contradiction (00:13:03 "signed April 1" vs. 00:14:21; Flag 4 / O-6) — declaration cross-checked against the criminal-trial testimony | Dr. Rahman | Substantive (1 of 2) | Until resolved, the biggest compensatory line ($1.05M–$1.12M DOCUMENTED-PENDING/ASSERTED) and the "13 days" narrative cannot be used externally (Move 3) |
| W8 | Paper the damages model (Move 3): economist retention for front pay ($700K–$3.5M ESTIMABLE — expert required), pharmacy records for the $4,000-a-bottle medication (ESTIMABLE → upgrade to DOCUMENTED via pharmacy records; per-bottle price is a client statement), psych corroboration for distress ($100K–$1.25M ESTIMABLE, NYSHRL/NY-torts only) | Drazen | Counsel | Each record upgrade ratchets the defensible Tier 2 mid upward |
| W9 · Sep 28–Oct 4 | Light: review defendants' academic-record production against his own set (discrepancy check vs. the DA-produced set) — only if produced; otherwise nothing | Dr. Rahman | Light | Production review only becomes possible now; keeps the week light |
| W9 | Review productions; build the spoliation record (never-produced ANSCO CCTV); motion to compel if needed | Drazen | Counsel | Leverage index moves ~6.5/10 → ~8/10 if the academic record, CCTV, and texts land before mediation |
| W10 · Oct 5–11 | Damages-documentation follow-ups (one sitting): remaining paternal-loan wires; confirm the DOCUMENTED set (medical bills $40K + Cornell $13K + car $44K + civil legal $35K) and ESTIMABLE upgrades (travel $40K, meds ≤$180K, ICD-gap ≤$50K, mother's salary ≤$71K, board fee ≤$2.5K) | Dr. Rahman | Substantive (1 of 2) | Completes the Tier 1 floor ($1.22M–$1.60M DOCUMENTED/ESTIMABLE) before the mediation statement freezes |
| W10 | Assemble the mediation-statement number architecture: Tier 1 $1.22M–$1.60M (floor/BATNA) / Tier 2 $4.34M–$16.57M ESTIMABLE (where the mediator prices) / model-implied zone $2M–$7M today, $5M–$12M if discovery + amendments land | Drazen | Counsel | Anchor with architecture, not a naked number (O-27) |
| W10 | Second courier pass for any remaining wire/expense records | Haseeb | Family channel | Closes the financial-records loop |
| W11 · Oct 12–18 | Light buffer week. Nothing scheduled | Dr. Rahman | Light | Deliberate buffer before the emotionally heavy mediation-prep weeks |
| W11 | Mediator selection/logistics; continue production fights | Drazen | Counsel | DZ-03 sequencing |
| W12 · Oct 19–25 | Mediation prep session 1 — non-monetary must-haves lead: record correction/expungement, board-safe verification letters, USCIS-usable stipulation, neutral-reference protocol, institutional-change component (treated as equivalent to the first several million dollars in any trade-off). Alone this week. | Dr. Rahman + Drazen | Heavy-emotional (alone) | Revisiting the narrative is heavy; non-monetary demands are the client's true first-order objective and open the mediation plan |
| W12 | Finalize mediation statement; prepare the GML 50-e(5) late-notice decision (option closes ~Dec 2026 — decide by Nov) | Drazen | Counsel | Both November decisions staged |
| W13 · Oct 26–Nov 1 | Light recovery week. ICD/medication adherence check-in before mediation month | Dr. Rahman | Health / Light | Mandatory light week after W12; arrive at mediation with the health floor intact |
| W13 | Number-architecture alignment call with the client: $100M = NEGOTIATION POSTURE ONLY; $40M = acceptance threshold (client directive) — both ASSERTED, Rule 11 / mediator-credibility caveat on every use; counsel must own the gap between $40M and the defensible Tier 2 top ($16.57M) before mediation (O-27: posture figure used once, by counsel, in caucus, immediately tied back to components — never as our valuation) | Drazen (with Dr. Rahman) | Counsel + Light (client side) | MASTER_LEGAL_PLAN requires counsel to own the gap with the client before mediation |
| W14 · Nov 2–8 | Mediation prep session 2: caucus roles, Q&A run-through, Tier 1 receipts → argue in Tier 2 → Tier 3 (~$100M ASSERTED/POSTURE) once, in caucus, as carrier tail risk only | Dr. Rahman + Drazen | Substantive (1 of 2) | Final rehearsal inside the pacing cap |
| W14 | Pre-mediation gate check (DZ-03): amendment granted, defendants' discovery responses in hand, spoliation record assembled — Drazen will not mediate without the responses | Drazen | Counsel | The governing sequencing principle |
| W15–16 · Nov 9–22 | Court-ordered mediation session(s) — must be completed by November 2026 (DZ-03). Faraaz's calendar cleared of everything else; lead with the non-monetary demand set | All (Drazen leads; Haseeb attends as family support) | Substantive (only item) | Clock #2 — the November deadline |
| W17 · Nov 23–29 | Rest week — no litigation tasks | Dr. Rahman | Health / Rest | The envelope closes with recovery, not a task |
| W17 | Post-mediation follow-through; execute the GML 50-e(5) late-notice decision (closes ~Dec 2026) | Drazen | Counsel | The only remaining clock is counsel's, not the client's |

Completed / non-scheduled items: FR-08 (CCTV poster image) — completed during the Aug 2 call (01:10:28). FR-09 — unclear_referent; resolved by the W2 clarification call, not scheduled as work. FAM-01 — standing logistics (Verizon phone), not a slot.

Standing honesty note: No deadline was stated on the call for any item except the November 2026 mediation completion (DZ-03) and Drazen's unspecified schedule deadline (DZ-01); all week assignments above are sequencing choices under the pacing rules, not court deadlines. All probabilities and leverage estimates referenced are subjective estimates from strategy/MASTER_LEGAL_PLAN.md; counsel review required before any element is used externally.

Attorney Work Product — Privileged & Confidential.